Book Marketing & Syndication Plan

Community-First Distribution Strategy

for

Rust Blockchain: A Full-Stack Implementation Guide

From Whitepaper to Production

March 2026 — Updated

# Table of Contents

1.  Strategy: Write Once, Distribute Everywhere

2.  Storefront Strategy (Amazon KDP + Gumroad + Leanpub)

3.  Pricing Strategy & KDP Royalty Guide

4.  Rust Community Channels

5.  Blog Content Strategy

6.  Lead Magnets: Blog Posts, Cheat Sheets & GitHub Templates

7.  Syndication Playbook (Hashnode, Dev.to, Medium)

8.  Advanced Reader Copies (ARC) & Influencer Outreach

9.  SEO & Discoverability

10. Launch Timeline

11. Content Calendar (First 8 Weeks)

12. Metrics & Success Criteria

13. Action Checklist

# 1. Strategy: Write Once, Distribute Everywhere

Rust developers are highly active in specific, centralized digital spaces that prioritize technical depth. The strategy operates on a hub-and-spoke model:

The Hub (Personal Blog): Hashnode on a custom domain. You own the SEO and the audience. The Spokes (Syndication): Cross-post to Dev.to and Medium. Use canonical tags to point back to the hub. The Storefronts: Amazon KDP (print + Kindle), Gumroad (digital, highest margin), Leanpub (technical audience, variable pricing). The CTA: Every technical post ends with a clear link to your sales page.

This model works because each layer serves a different purpose: the hub builds SEO authority and an email list you own, the spokes provide reach into existing developer audiences, the storefronts handle transactions, and the CTA converts readers into buyers.

# 2. Storefront Strategy

## 2.1 Amazon KDP

Handles: Print-on-demand paperback, Kindle eBook, global distribution, Amazon search ranking.

- Paperback: Upload print-ready PDF interior + cover PDF. KDP prints and ships on demand. No inventory. Pricing: $49.99–$59.99 (print cost ~$8–12 for 730 pages).

- Kindle: Upload ePub or KPF. Pricing: $29.99–$39.99.

- KDP Select: Do NOT enroll. KDP Select requires Kindle exclusivity, blocking Gumroad and Leanpub eBook sales.

- Categories: “Computers & Technology > Programming Languages > Rust” and “Computers & Technology > Blockchain & Cryptocurrencies.”

- Keywords (use all 7 slots): “Rust programming book”, “blockchain Rust”, “Axum web framework”, “Tauri 2 desktop app”, “Bitcoin implementation”, “full-stack Rust”, “Iced GUI Rust.”

## 2.2 Gumroad

Handles: Direct digital sales. You keep ~90%. Direct customer relationship. Email list building.

- Tier 1 — Standard: PDF + ePub bundle. $39.99.

- Tier 2 — Premium: PDF + ePub + complete source code repository access. $59.99.

- Tier 3 — Team: 5-seat license at a discount. $149.99.

- Landing page: Cover image, technology list, table of contents, and a free PDF sample (Chapter 0 + Chapter 1).

## 2.3 Leanpub

Handles: Technical book marketplace. 80% royalty. Variable pricing. Built-in web reader. “Publish as you write” model.

- Variable pricing: Minimum $29.99, suggested $44.99. Readers often pay above minimum for quality technical content.

- Incremental publishing: Publish early chapters now, update as LaTeX conversion completes. Leanpub is built for this.

- Web reader: Readers can read online without downloading — a “try before you commit” experience.

# 3. Pricing Strategy & KDP Royalty Guide

## 3.1 Price Matrix

| Product | Amazon | Gumroad | Leanpub | Notes |
| --- | --- | --- | --- | --- |
| Paperback | $54.99 | — | — | Amazon only (POD) |
| Kindle eBook | $9.99 | — | — | Priced for 70% royalty tier |
| Digital (PDF+ePub) | — | $39.99 | $29.99–$44.99 | Higher margin platforms |
| Premium + source | — | $59.99 | — | Gumroad exclusive |
| Team (5 seats) | — | $149.99 | — | Gumroad exclusive |

## 3.2 Amazon KDP Royalty Breakdown

Amazon offers two royalty tiers for Kindle eBooks. Understanding these is critical for pricing:

| Royalty | Price Range | You Keep | Constraints |
| --- | --- | --- | --- |
| 70% | $2.99 – $9.99 | ~$7.00 on $9.99 book | Must opt into delivery fee (~$0.15/MB) |
| 35% | $0.99 – $200 | ~$12.25 on $34.99 book | No price restriction, no delivery fee |

Recommendation: Price the Kindle edition at $9.99 to qualify for the 70% royalty tier (~$7.00 per sale). This is lower than the Gumroad/Leanpub price, which is intentional — Amazon’s role is discoverability and reviews, not maximum revenue. Buyers who want the premium experience (PDF, ePub, source code) go to Gumroad at $39.99–$59.99. The Kindle price drives volume, reviews, and Amazon search ranking, which feeds traffic to your blog, which feeds Gumroad/Leanpub sales.

Paperback royalty: 60% minus printing cost. For a 730-page book at $54.99, estimated print cost is ~$10. Your royalty: ~$23 per paperback sale.

# 4. Rust Community Channels

Directly engaging where Rustaceans spend time is the most effective way to build social proof, earn reviews, and drive word-of-mouth. These are the highest-impact channels:

## 4.1 This Week in Rust (Top Priority)

This is the single most important channel in the Rust ecosystem. This Week in Rust is a weekly newsletter reaching tens of thousands of active Rust developers. You can submit blog posts and book announcements to be featured. A mention here puts your book in front of the exact audience you need. Submit at: https://this-week-in-rust.org/

- Submit your launch announcement post for the week of publication.

- Submit each syndicated blog post as it goes live — they accept “Rust blog posts” as a category.

- Aim for at least 3–4 features over the first 2 months.

## 4.2 Reddit r/rust

- Launch post: Write a genuine “why I wrote this book and how it’s different” post. r/rust respects authenticity and dislikes pure promotion. Lead with value (what you learned, interesting technical decisions), mention the book naturally.

- Chapter excerpts: Share individual blog posts with discussion-inviting titles. “We built the same desktop app in Iced and Tauri — here’s what we learned” performs better than “Check out my book.”

- AMA: Consider a “I wrote a 730-page Rust book, AMA” post after launch. High engagement format.

## 4.3 Rust Users Forum

users.rust-lang.org is a high-intent community. Post your book under the “Announcements” category. Keep it factual — what the book covers, who it’s for, where to get it. This audience is receptive to well-documented technical resources.

## 4.4 Discord Servers

- The Rust Programming Language (official): Large server with channels for learning resources.

- Rust Community: Active discussion server.

- Framework-specific servers: Iced, Tauri, and Tokio each have Discord communities. Sharing chapters relevant to their framework is well-received and on-topic.

## 4.5 Hacker News

- Submit the Iced vs Tauri comparison post and the Axum tutorial — these have the broadest appeal beyond just the Rust community.

- Time submissions for US morning (9–11am ET) for maximum visibility.

- If the post gains traction, engage with every comment.

# 5. Blog Content Strategy

Every post should be genuinely useful on its own — not a teaser that withholds value. Readers who get real value from a free post are the ones who buy the book.

## 5.1 Blog Post Types

- Type 1: Chapter Excerpt (modified). Take a chapter’s core concept and rewrite it as a standalone blog post. Not a copy-paste — restructure for the blog format. Example: “How We Implemented UTXO Tracking in Rust” from Chapter 9.

- Type 2: Framework Comparison. The Iced vs Tauri side-by-side is unique content nobody else has. “Iced vs Tauri 2: Building the Same Desktop App in Pure Rust and Rust+React.”

- Type 3: Tutorial/How-To. Standalone tutorials derived from the book. “Building a REST API with Axum: Auth, CORS, and OpenAPI” or “Encrypted Local Storage with SQLCipher in Rust.”

- Type 4: Architecture Deep-Dive. System-level posts. “From Bitcoin Whitepaper to Running Blockchain in 5 Minutes.”

## 5.2 Where to Host the Primary Blog

Host the canonical version on Hashnode with a custom domain (e.g., blog.fullstackrust.com or fullstackrust.dev/blog). Hashnode offers built-in SEO, developer audience, newsletter functionality, and no paywall friction. This builds your brand’s search authority over time.

# 6. Lead Magnets: Blog Posts, Cheat Sheets & GitHub Templates

## 6.1 Blog Post Lead Magnets (ranked by traffic potential)

| # | Post Title | Source | Type | Traffic |
| --- | --- | --- | --- | --- |
| 1 | Iced vs Tauri 2: Same App, Two Architectures | Ch 16–19 | Comparison | Very High |
| 2 | Building a REST API with Axum: Auth, CORS & OpenAPI | Ch 15 | Tutorial | Very High |
| 3 | From Whitepaper to Running Blockchain in 5 Minutes | Ch 0–1 | Architecture | High |
| 4 | Encrypted Local Storage with SQLCipher in Rust | Ch 20 | Tutorial | High |
| 5 | How Bitcoin’s UTXO Model Works (in Rust) | Ch 9–10 | Excerpt | High |
| 6 | Deploying a Rust Blockchain with Docker Compose | Ch 22 | Tutorial | Medium |
| 7 | Building Desktop Apps with Iced: Pure Rust MVU | Ch 16 | Tutorial | Medium |
| 8 | Tauri 2 IPC Deep Dive: Bridging Rust and React | Ch 17 | Tutorial | Medium |

## 6.2 Downloadable Lead Magnets (Email Capture)

These require an email signup via your blog, building a mailing list you own — independent of any platform.

- Rust + Blockchain Cheat Sheet (PDF): A 2–4 page reference card covering the key data structures, traits, and patterns used in the book. Include the Block struct, Transaction fields, UTXO lifecycle, and key crypto operations. Hosted on Gumroad as a free product ($0) that captures email.

- Project Starter Template (GitHub): A minimal Rust workspace template mirroring the book’s crate structure (blockchain core, API, wallet) with placeholder modules. Developers clone it and fill in the implementations as they read. Link to the GitHub repo from your blog; require email signup to get the companion setup guide.

- Free Sample Chapters (PDF): Chapter 0 (Quick Start) + Chapter 1 (Introduction) as a polished PDF. Shows the quality of the full book. Hosted on Gumroad as a free download.

## 6.3 Call-to-Action Template

Every blog post ends with this block:

This post is adapted from Rust Blockchain: A Full-Stack Implementation Guide — a 24-chapter, 730-page book covering Axum, Iced, Tauri 2, Tokio, SQLCipher, Docker, and Kubernetes through one cohesive project. Get the book: Amazon (paperback + Kindle) ¦ Gumroad (PDF + source code) ¦ Leanpub (pay what you want) Free resources: Download the Rust+Blockchain Cheat Sheet ¦ Clone the Starter Template

# 7. Syndication Playbook

### Hashnode (Canonical Home)

- Publish here first. All syndicated copies set the canonical URL to this version.

- Tags: rust, blockchain, axum, tauri, iced, web-development

- Create a “Rust Blockchain” series linking all posts together.

- Enable Hashnode’s built-in newsletter for subscriber notifications.

### Dev.to

- Cross-post within 24 hours. Use the “canonical URL” field pointing to Hashnode.

- Tags: rust, blockchain, webdev, tutorial (max 4).

- End posts with a discussion question to boost engagement.

### Medium

- Cross-post 2–3 days after Hashnode (let canonical get indexed first).

- Submit to publications: “Better Programming”, “Level Up Coding.” Their audience becomes yours.

- Do NOT put posts behind the paywall. The goal is reach, not Medium revenue.

## Per-Post Syndication Workflow

- Day 0: Publish on Hashnode. Share on Twitter/X, Reddit (r/rust, r/bitcoin), and submit to This Week in Rust.

- Day 1: Cross-post to Dev.to with canonical URL. Engage with comments.

- Day 2–3: Import to Medium. Submit to a publication.

- Day 3–7: Monitor. Respond to every comment. Share on LinkedIn. Post in relevant Discord servers.

# 8. Advanced Reader Copies & Influencer Outreach

Sending free early copies to influential Rust developers is the highest-leverage launch activity. A single mention from a respected voice can drive more sales than weeks of blog syndication.

## 8.1 Target Influencers

| Who | Platform / Reach | Why |
| --- | --- | --- |
| Jon Gjengset | YouTube (Crust of Rust), Twitter. 100K+ followers. | Most respected Rust educator. A mention is gold. |
| fasterthanlime | Blog (fasterthanli.me), Twitter. Massive Rust audience. | Deep-dive technical writing. Perfect alignment. |
| This Week in Rust editors | Newsletter. Tens of thousands of subscribers. | Can feature the book as a “new resource.” |
| Rust subreddit moderators | r/rust. 250K+ members. | Can pin or highlight launch post. |
| Iced maintainer (Héctor Ramón) | GitHub, Twitter. | Would appreciate chapters 16/18 showcasing Iced. |
| Tauri team | Discord, Twitter, GitHub. | Would appreciate chapters 17/19 showcasing Tauri 2. |
| Tokio maintainers | Discord, Twitter. | Async runtime is central to the book. |

## 8.2 ARC Strategy

- Prepare ARCs 2–3 weeks before launch. Send a polished PDF with a personal note explaining why their feedback matters.

- Ask for an honest review. Do not ask for a positive review — ask for an honest one. Authenticity matters in the Rust community.

- Make it easy. Include a 2–3 sentence summary they can copy/paste as a blurb if they want to endorse it.

- Follow up once. A gentle reminder 1 week after sending. No more than that.

Template email: “Hi [Name], I’ve written a 730-page book that teaches Axum, Iced, Tauri 2, Tokio, and more through building a complete Bitcoin blockchain in Rust. I think it aligns well with your work on [their project/content]. I’d love to send you an early copy for an honest review. No obligation. Here’s a free PDF: [link]. Thank you for your time.”

# 9. SEO & Discoverability

## 9.1 Target Keywords

| Keyword | Volume | Competition |
| --- | --- | --- |
| rust blockchain | Medium | Low |
| axum tutorial | Medium | Low |
| tauri 2 rust react | Medium | Very Low |
| iced rust gui | Low–Medium | Very Low |
| rust bitcoin implementation | Low–Medium | Low |
| sqlcipher rust | Low | Very Low |
| iced vs tauri | Low | Very Low |
| full stack rust | Low | Very Low |

Most keywords have low competition because the Rust ecosystem is growing. Early, high-quality content ranks quickly.

## 9.2 Amazon A9 Algorithm

Amazon ranks books by relevance (keywords, categories) and sales velocity. Blog syndication drives external traffic to your Amazon listing, boosting velocity, which improves ranking — a virtuous cycle. The $9.99 Kindle price drives volume; volume drives reviews; reviews drive organic Amazon sales.

# 10. Launch Timeline

| Week | Action | Status |
| --- | --- | --- |
| Week −4 | Complete LaTeX conversion. Finalize cover. Prepare print-ready PDFs. | Pending |
| Week −3 | Set up KDP, Gumroad, Leanpub. Create product pages. Prepare ARC PDFs. | Pending |
| Week −2 | Send ARCs to 5–7 influencers. Write blog posts #1–2. Set up Hashnode. Create cheat sheet + starter template. | Pending |
| Week −1 | Publish post #1 (Iced vs Tauri). Syndicate. Submit to This Week in Rust. Build anticipation. | Pending |
| LAUNCH | Publish on all 3 platforms. Post #2 (Axum). 20% discount. Reddit/HN/Twitter/LinkedIn. Email newsletter. | Pending |
| +1 | Post #3. Syndicate. Submit to This Week in Rust. Engage all comments. | Pending |
| +2 | Post #4. Request reviews from early buyers. End launch discount. Follow up with ARC recipients. | Pending |
| +3 to +8 | 1 post/week (posts #5–10). Continue syndication. Submit each to TWiR. Track per-post conversions. | Pending |

# 11. Content Calendar (First 8 Weeks)

| Wk | Blog Post | Syndicate | Promote |
| --- | --- | --- | --- |
| Pre | Iced vs Tauri 2: Same App, Two Architectures | HN, Dev.to, Medium | r/rust, TWiR |
| 0 | Building a REST API with Axum | Dev.to, Medium | Reddit, Twitter, LI |
| 1 | Whitepaper to Blockchain in 5 Minutes | Dev.to, Medium | r/bitcoin, HN |
| 2 | Encrypted Storage with SQLCipher in Rust | Dev.to, Medium | Twitter thread |
| 3 | Bitcoin UTXO Model in Rust | Dev.to, Medium | HN, r/rust, TWiR |
| 4 | Docker Compose Blockchain Deployment | Dev.to, Medium | r/devops, r/docker |
| 5 | Desktop Apps with Iced: Pure Rust MVU | Dev.to, Medium | r/rust, Iced Discord |
| 6 | Rust Crypto: SHA-256, ECDSA, Keys | Dev.to, Medium | Twitter, TWiR |
| 7 | Kubernetes for Rust Developers | Dev.to, Medium | r/kubernetes |
| 8 | Tauri 2 IPC: Bridging Rust and React | Dev.to, Medium | Tauri Discord, r/tauri |

# 12. Metrics & Success Criteria

| Metric | Month 1 | Quarter 1 |
| --- | --- | --- |
| Book sales (all platforms) | 50–100 | 200–500 |
| Blog views (all platforms) | 5,000–10,000 | 25,000–50,000 |
| Amazon reviews | 5–10 | 20–30 |
| Email subscribers | 100–200 | 500–1,000 |
| Gumroad revenue | $500–$1,500 | $2,000–$5,000 |
| This Week in Rust features | 1–2 | 4–6 |

Track blog-to-sale conversion using unique Gumroad discount codes per post.

# 13. Action Checklist

## Phase 1: Setup (Week −4 to −3)

- Complete LaTeX conversion and generate print-ready PDF

- Finalize cover (Midjourney + Canva)

- Create Amazon KDP account; upload paperback + Kindle

- Create Gumroad account; set up 3-tier product page

- Create Leanpub account; set up variable pricing

- Set up Hashnode blog on custom domain

- Create Dev.to and Medium accounts

- Prepare free PDF sample (Ch 0 + Ch 1) for Gumroad

- Create Rust+Blockchain cheat sheet (PDF)

- Create GitHub starter template repository

## Phase 2: Pre-Launch (Week −2 to −1)

- Send ARC PDFs to 5–7 influencers with personalized emails

- Write blog post #1: Iced vs Tauri 2 comparison

- Write blog post #2: Axum REST API tutorial

- Publish post #1 on Hashnode; syndicate to Dev.to and Medium

- Submit post #1 to This Week in Rust

- Share post #1 on Reddit r/rust and Twitter/X

- Set up email capture on blog (Hashnode newsletter + Gumroad free downloads)

## Phase 3: Launch (Week 0)

- Publish book on Amazon KDP, Gumroad, and Leanpub simultaneously

- Activate 20% launch discount on all platforms

- Publish blog post #2 with book CTA

- Submit launch announcement to This Week in Rust

- Post on Rust Users Forum (Announcements category)

- Post on Reddit r/rust, r/bitcoin, r/programming

- Submit to Hacker News

- Share on Twitter/X and LinkedIn with cover image

- Post in Iced, Tauri, and Tokio Discord servers

- Email Hashnode newsletter subscribers

## Phase 4: Post-Launch (Weeks +1 to +8)

- Publish 1 blog post per week per content calendar

- Syndicate each post within 72 hours

- Submit each post to This Week in Rust

- Request reviews from early buyers (week +2)

- End launch discount (week +2)

- Follow up with ARC recipients (week +2)

- Track per-post conversion with unique Gumroad codes

- Review metrics monthly; adjust calendar based on performance

Total estimated cost: $10 (Midjourney) + $0 (Canva, KDP, Gumroad, Leanpub, Hashnode) = $10. Estimated first-quarter revenue: $2,000–$8,000+ across all platforms.

— End of Document —