PUBLICATION LAUNCH GUIDE

────────────────────────────────────────

Rust Blockchain: A Full-Stack Implementation Guide

Bill Kunyiha

Prepared: March 22, 2026

Version 1.1

# Table of Contents

1.  Book Specifications & Deliverables

2.  ISBN & Metadata Configuration

3.  IngramSpark Print Upload

4.  Ordering & Reviewing the Proof Copy

5.  Amazon KDP (Kindle & Paperback)

6.  Apple Books Upload

7.  Other Distribution Channels

8.  Pricing & Royalty Summary

9.  Pre-Launch Marketing Checklist

10.  Launch Day Checklist

11.  Post-Launch Monitoring

12.  Appendix: File Inventory

# Current Status & Remaining Steps

This section tracks the overall publication progress. Last updated: March 22, 2026.

| Step | Status | Details |
| --- | --- | --- |
| Book files generated | COMPLETE | Interior PDF, cover wrap, EPUBs all finalized |
| ISBNs registered | COMPLETE | Print: 979-8-9954311-1-4, E-book: 979-8-9954311-0-7 |
| IngramSpark print upload | COMPLETE | Title submitted, awaiting digital proof (3–5 days) |
| Digital proof review | WAITING | IngramSpark will email proof in 3–5 business days |
| Physical proof order & review | NOT STARTED | Order after approving digital proof (~$12.50 + shipping) |
| Amazon KDP Kindle upload | NOT STARTED | Upload rust-blockchain-kindle.epub, price at $9.99 |
| Apple Books upload | NOT STARTED | Upload rust-blockchain.epub, price at $9.99 |
| Other platforms (optional) | NOT STARTED | Leanpub, Google Play, Kobo, Gumroad |
| Pre-launch marketing | NOT STARTED | Landing page, community posts, review copies |
| Enable IngramSpark distribution | NOT STARTED | Only after physical proof is approved |
| Launch day coordination | NOT STARTED | Go live on all platforms simultaneously |

ACTION ITEMS Immediate next steps (do now, while waiting for IngramSpark digital proof): 1. Upload Kindle e-book to Amazon KDP (Section 5) 2. Upload e-book to Apple Books (Section 6) 3. Begin pre-launch marketing activities (Section 9)

# 1. Book Specifications & Deliverables

The following specifications and files represent the final, print-ready state of the book after all QA passes, LaTeX compilation, and format generation.

## 1.1 Physical Book Specifications

| Attribute | Value |
| --- | --- |
| Title | Rust Blockchain: A Full-Stack Implementation Guide |
| Author | Bill Kunyiha |
| Trim Size | Crown Quarto — 7.44″ × 9.69″ |
| Interior Pages | 696 pages (348 sheets) |
| Paper Stock | Cream 60 lb (natural, easy on the eyes for long reads) |
| Binding | Perfect bound (paperback) |
| Cover Finish | Glossy laminate |
| Interior Color | Black & white (standard) |
| Spine Width | 1.12″ (calculated for cream 60 lb at 696 pages) |
| Bleed | 0.125″ on all sides |

## 1.2 Final Deliverable Files

| File | Purpose | Size | Details |
| --- | --- | --- | --- |
| interior.pdf | Print interior | 13 MB | 696 pages, crop marks, 7.69″×9.94″ with bleed |
| cover-full-wrap.pdf | IngramSpark cover | 1.6 MB | Front + spine (1.12″) + back |
| cover-full-wrap.png | Cover wrap (PNG) | 13 MB | 4876×2983 px at 300 DPI |
| cover-front.png | Front cover only | 6.3 MB | For marketing and store listings |
| cover-back.png | Back cover only | 6.4 MB | With ISBN barcode |
| rust-blockchain.epub | E-book (highlighted) | 22 MB | Tango syntax highlighting |
| rust-blockchain-kindle.epub | Kindle-optimized | 21 MB | Plain monospace (no highlighting) |

Note: File Location All deliverable files are located in the book-print/ directory. The interior PDF has crop marks enabled and the back cover removed — IngramSpark handles the cover separately via the cover wrap file.

# 2. ISBN & Metadata Configuration

Each format of the book requires its own unique ISBN. This is a publishing industry requirement — a single ISBN cannot be shared across print and digital editions.

## 2.1 ISBN Assignments

| Format | ISBN | Registered At |
| --- | --- | --- |
| Print (Paperback) | 979-8-9954311-1-4 | myidentifiers.com |
| E-Book (EPUB) | 979-8-9954311-0-7 | myidentifiers.com |

Tip: Future Formats If you plan to release a hardcover edition in the future, you will need a third ISBN. Audiobook editions also require a separate ISBN. Purchase additional ISBNs at myidentifiers.com (Bowker). Buying in bulk (10-pack) is significantly cheaper per unit than individual purchases.

## 2.2 Metadata Checklist

Ensure the following metadata is consistent across all platforms:

☐  Title: Rust Blockchain: A Full-Stack Implementation Guide

☐  Author: Bill Kunyiha

☐  Publisher: (your imprint name if applicable)

☐  Language: English

☐  BISAC Codes: COM051360 (Blockchain), COM051010 (Programming / General)

☐  Description / blurb: consistent across all stores

☐  Keywords: Rust, blockchain, cryptocurrency, smart contracts, distributed systems, full-stack

☐  Publication date: set to your planned launch date

# 3. IngramSpark Print Upload

IngramSpark is the primary print-on-demand platform, providing distribution to Amazon, Barnes & Noble, independent bookstores, and libraries worldwide.

## 3.1 Account Setup

☐  Create account at ingramspark.com (if not already done)

☐  Complete publisher profile with contact and payment information

☐  Set up direct deposit for royalty payments

## 3.2 Title Setup

Navigate to "Add a New Title" and enter the following:

| Field | Value |
| --- | --- |
| Print ISBN | 979-8-9954311-1-4 |
| Title | Rust Blockchain: A Full-Stack Implementation Guide |
| Author | Bill Kunyiha |
| Publishing Rights | I own the copyright or hold necessary publishing rights |
| Imprint | Your imprint name (use consistently across all platforms and Bowker) |
| Full Description | See Section 3.2.1 below |
| Short Description | See Section 3.2.2 below |
| Keywords | See Section 3.2.3 below |
| BISAC Subjects | COM091000; COM051360; COM051010 |
| Thema Subjects | UFL; UFB; UM |
| Thema Qualifiers | 2ACR (English); 4CP (Professional/Specialist) |
| Trim Size | Crown Quarto — 7.44″ × 9.69″ |
| Interior Color | Color 50 |
| Paper Color | Cream |
| Binding Type | Perfect Bound — Glued Spine with Color Laminated Cover (Gloss) |
| Duplex (Interior) | Enabled (two-sided printing) |
| Duplex (Cover) | Disabled (single-sided cover is standard for paperbacks) |
| Page Count | 696 |
| Market | Global |

### 3.2.1 Full Description

Rust Blockchain: A Full-Stack Implementation Guide takes you from zero to a fully functional blockchain system built entirely in Rust. Across 33 chapters and 696 pages, this hands-on guide covers everything from cryptographic primitives and consensus algorithms to smart contracts, peer-to-peer networking, and wallet development.

Whether you are a Rust developer exploring blockchain technology or a blockchain engineer looking to leverage Rust’s performance and safety guarantees, this book provides a complete, production-oriented implementation you can follow from start to finish. Each chapter builds on the last, with working code, architectural explanations, and real-world design decisions throughout.

Topics include SHA-256 hashing and digital signatures, proof-of-work and proof-of-stake consensus, Merkle trees and transaction verification, a full networking layer with peer discovery, smart contract execution, wallet and key management, a REST API layer, and comprehensive testing strategies.

### 3.2.2 Short Description

A comprehensive, hands-on guide to building a complete blockchain system from scratch using Rust. Covers cryptography, consensus, smart contracts, networking, wallets, and APIs across 33 chapters.

### 3.2.3 Keywords

Enter as semicolon-separated values (228 characters, under the 500-character limit):

Rust programming;blockchain development;cryptocurrency;smart contracts;distributed systems;peer-to-peer networking;consensus algorithms;proof of work;proof of stake;systems programming;Rust language;blockchain architecture;decentralized applications;full-stack development

## 3.3 File Upload

☐  Upload interior.pdf — Interior file:

This is the 696-page interior with crop marks and 0.125″ bleed. The back cover is not included — IngramSpark handles covers separately.

☐  Upload cover-full-wrap.pdf — Cover file:

This is the full cover wrap (front + 1.12″ spine + back) at 300 DPI with 0.125″ bleed on all edges.

## 3.4 Preflight Check

IngramSpark runs an automated preflight check on your uploaded files. Common issues to watch for:

| Potential Issue | Resolution |
| --- | --- |
| Image resolution below 300 DPI | All images in the LaTeX build are vector or high-res; should pass |
| Spine text misalignment | Spine was generated at exact 1.12″ width; verify in proof |
| Bleed area missing content | Crop marks and bleed are set in preamble.tex; should pass |
| Color space warnings | Interior is B&W; cover uses RGB which IngramSpark accepts |
| Font embedding issues | LaTeX embeds all fonts by default; should pass |

Warning: If Preflight Fails If the preflight check flags any issues, do not guess at fixes. Note the exact error messages and we can address them in the LaTeX source or generation scripts.

## 3.5 Distribution Settings

IngramSpark offers global distribution. Recommended settings:

Configure pricing, wholesale discount, and return policy for each market:

| Market | Currency | Retail Price | Wholesale Discount | Returns |
| --- | --- | --- | --- | --- |
| United States | USD | $49.99 | 40% | Non-Returnable |
| United Kingdom | GBP | £39.99 | 40% | Non-Returnable |
| European Union | EUR | €46.99 | 40% | Non-Returnable |
| Canada | CAD | $64.99 | 40% | Non-Returnable |
| Australia | AUD | $74.99 | 40% | Non-Returnable |
| Sharjah | USD | $49.99 | 40% | Non-Returnable |
| Global Connect | USD | $49.99 | 40% | Non-Returnable |

Pricing Notes The 40% wholesale discount is the minimum IngramSpark requires for retailer distribution. Some authors go to 55% to incentivize physical bookstores to stock the title, but for a niche technical book where most sales will be online, 40% keeps your margins higher. Non-returnable is standard for print-on-demand titles — accepting returns means bookstores can send unsold copies back at your cost.

Additional distribution settings:

☐  Enable all distribution channels: Amazon, B&N, Ingram catalog, library distributors

☐  Set territory rights: Worldwide

☐  Do NOT approve for distribution until you have reviewed a physical proof copy

## 3.6 IngramSpark E-Book Distribution (Skip)

IngramSpark offers e-book distribution through its title setup, with options including Amazon (Ebook), Apple (Ebook), and Lightning Source Sharjah. Here is the recommended approach for each:

| Channel | Recommendation | Reason |
| --- | --- | --- |
| Amazon (Ebook) | SKIP — upload directly to KDP | Direct KDP upload gives 70% royalty (vs. IngramSpark wholesale terms), plus access to KDP promotions like Kindle Countdown Deals and Kindle Unlimited enrollment |
| Apple (Ebook) | SKIP — upload directly to Apple Books | Direct upload via Apple Books for Authors gives 70% royalty and faster publishing turnaround, versus IngramSpark as a middleman |
| Lightning Source Sharjah | ENABLE for print | This is Ingram’s printing facility in the UAE, serving the Middle East, India, and parts of Asia. Enabling it reduces shipping times and costs for readers in those regions |

Key Principle: Direct E-Book Distribution As a general rule, upload e-books directly to each platform (KDP, Apple Books) to maximize royalties and control. Use IngramSpark primarily for its print-on-demand distribution network, which is where its real strength lies — getting your paperback into bookstores, libraries, and international markets you cannot easily reach on your own.

# 4. Ordering & Reviewing the Proof Copy

CRITICAL STEP This is the single most important quality gate before publication. Never approve a title for distribution without holding the physical book in your hands.

## 4.1 Post-Upload Timeline

After uploading your files to IngramSpark, the process follows this timeline:

| Step | Timeline | Action Required |
| --- | --- | --- |
| Digital proof delivery | 3–5 business days | IngramSpark emails a digital proof PDF for review |
| Review and approve digital proof | 1–2 days (your review time) | Check cover alignment, spine text, interior pages |
| Order physical proof copy | After digital approval | Order a print copy (~$12.50 + shipping) |
| Review physical proof | 5–10 days (shipping + review) | Use the detailed checklist in Section 4.2 |
| Enable distribution | After physical approval | Book propagates to retailers in 6–8 weeks |

Tip: Use the Waiting Period While waiting for the digital proof (3–5 days), use this window to upload e-books to Amazon KDP and Apple Books (Sections 5 and 6), and begin pre-launch marketing (Section 9). This way everything can go live around the same time.

## 4.2 Ordering the Physical Proof

Once you approve the digital proof, order a physical proof copy from IngramSpark. The cost is approximately $12.50 (printing cost) plus shipping. Select the fastest shipping option — this is worth the few extra dollars to avoid delays.

## 4.3 What to Check

When the proof arrives, review it systematically using the following checklist:

### Cover & Binding

☐  Front cover image is sharp and colors are accurate

☐  Spine text is centered, readable, and not cut off

☐  Back cover text is legible and properly positioned

☐  ISBN barcode on back cover scans correctly (use a phone barcode scanner app)

☐  Binding is secure — no loose pages

☐  Cover laminate is smooth with no bubbles or peeling

### Interior Content

☐  Page margins are even and consistent throughout

☐  No text is cut off at any edge (crop marks trimmed correctly)

☐  Code listings are legible and properly formatted

☐  Diagrams and figures are sharp and not pixelated

☐  Chapter headings and page numbers are consistent

☐  Table of contents page numbers match actual content

☐  Index entries reference correct page numbers (spot-check at least 20)

☐  No blank pages appear where content should be

☐  Cream paper color is acceptable (not too yellow, not too white)

### Typography

☐  Body text is easily readable at the chosen font size

☐  No orphan or widow lines at page boundaries

☐  Footnotes appear on the correct pages

☐  List of Figures entries are accurate

Iteration Process If you find issues that require changes, fix them in the LaTeX source, rebuild the interior PDF, re-upload to IngramSpark, and order another proof. Each iteration costs ~$15 but is far cheaper than publishing with errors. Budget for 1–2 proof rounds.

# 5. Amazon KDP (Kindle & Paperback)

## 5.1 Kindle E-Book

Amazon Kindle Direct Publishing is the primary e-book distribution channel, reaching the largest e-reader market globally.

### Setup Steps

☐  Log in to kdp.amazon.com

☐  Click "Create a New Kindle eBook"

☐  Enter title, author, description, and keywords (match IngramSpark metadata)

☐  Set BISAC categories: Blockchain, Programming / General

☐  E-book file: Upload rust-blockchain-kindle.epub

☐  Cover image: Upload cover-front.png

☐  Enable DRM (recommended for technical books)

☐  Set publication date to match your overall launch date

### Kindle Pricing

| Setting | Recommended Value | Notes |
| --- | --- | --- |
| List Price | $9.99 | Maximum price in 70% royalty tier |
| Royalty Plan | 70% | Available for $2.99–$9.99 |
| Delivery Fee | ~$0.30 | Based on ~2 MB file size |
| Net Royalty | ~$6.69 per sale | After delivery fee deduction |

Why the Kindle-Specific EPUB? Use the Kindle-specific EPUB (rust-blockchain-kindle.epub) which uses plain monospace code formatting instead of syntax highlighting. Kindle devices render highlighted code inconsistently, and the plain version provides a better reading experience and smaller file size.

## 5.2 KDP Paperback (Optional)

Amazon KDP also offers print-on-demand paperbacks. However, since you are distributing through IngramSpark, your paperback will already appear on Amazon via Ingram’s distribution network. You have two options:

| Approach | Pros | Cons |
| --- | --- | --- |
| IngramSpark only | Single source of truth, wider distribution, library access | Slightly lower Amazon royalty, 6–8 week Amazon listing delay |
| KDP + IngramSpark | Higher Amazon royalty, faster Amazon listing, Buy Box priority | Must manage two platforms, potential listing conflicts |

Recommended: Dual Strategy Many authors use both: IngramSpark for bookstore/library distribution and KDP Print for Amazon-specific sales. If you go this route, do NOT enable Amazon distribution on IngramSpark to avoid listing conflicts. Use KDP Print with the same interior.pdf and a KDP-formatted cover (KDP provides a cover template tool).

# 6. Apple Books Upload

Apple Books is the second-largest e-book market. The syntax-highlighted EPUB provides the best reading experience on Apple devices with their high-resolution Retina displays.

## 6.1 Setup Steps

☐  Create an Apple Books for Authors account at authors.apple.com

☐  Complete tax and banking information

☐  Click "New Book" and enter metadata (match other platforms)

☐  E-book file: Upload rust-blockchain.epub (syntax-highlighted version)

☐  Cover image: Upload cover-front.png

☐  Set price: $9.99 (Apple takes 30%, you keep $6.99)

☐  Set territory: All territories

☐  Set publication date to match launch

☐  Submit for review (Apple reviews typically take 1–3 days)

# 7. Other Distribution Channels

Beyond Amazon and Apple, several other platforms can expand your reach, particularly in international markets and among developers who prefer DRM-free purchases.

| Platform | Format | Commission | Notes |
| --- | --- | --- | --- |
| Google Play Books | EPUB (highlighted) | 48% to Google | play.google.com/books/publish |
| Kobo | EPUB (highlighted) | 30% to Kobo | kobowritinglife.com |
| Leanpub | EPUB + PDF | 20% to Leanpub | Popular with developers, DRM-free |
| Gumroad | EPUB + PDF | 10% flat fee | Direct sales, full control |
| Author Website | EPUB + PDF | Payment processor fee only | Highest margin, build mailing list |

Developer-Friendly Platforms Leanpub and Gumroad are especially popular with technical authors because they support DRM-free distribution, variable pricing (pay-what-you-want), and direct reader relationships. Consider offering a bundle (EPUB + PDF) on these platforms for a premium price.

# 8. Pricing & Royalty Summary

The following pricing strategy is based on the detailed analysis in Pricing-Strategy.docx, updated for the final book specifications (696 pages, Crown Quarto, cream 60 lb).

## 8.1 Recommended Prices

| Format | List Price | Platform Fee / Cost | Your Royalty |
| --- | --- | --- | --- |
| Print (IngramSpark) | $49.99 | ~$12.50 print + 40–55% wholesale | $17.49–$22.49 |
| Kindle (Amazon) | $9.99 | $0.30 delivery + 30% | ~$6.69 |
| Apple Books | $9.99 | 30% | $6.99 |
| Leanpub | $19.99 minimum | 20% + fees | ~$15.59 |
| Direct Sales | $14.99–$19.99 | Payment processor ~3% | ~$14.50–$19.40 |

## 8.2 Revenue Projections

| Scenario | Est. First-Year Revenue | Key Assumptions |
| --- | --- | --- |
| Conservative | ~$4,522 | 50 print + 100 Kindle + 30 Apple + 20 Leanpub |
| Optimistic | ~$12,600 | 150 print + 300 Kindle + 100 Apple + 60 Leanpub |

## 8.3 Launch Discount Strategy

Consider offering a limited-time launch discount to build momentum and early reviews:

Kindle: $4.99 for first 2 weeks (still in 70% tier)

Print: Promotional code for $39.99 if platform supports it

Leanpub: Set minimum to $9.99 and suggested to $19.99 during launch

# 9. Pre-Launch Marketing Checklist

Start these activities 2–4 weeks before your publication date to build anticipation.

## 9.1 Online Presence

☐  Set up a landing page or author website with book details and purchase links

☐  Create a "Coming Soon" announcement with cover image

☐  Prepare a book trailer or short demo video showing code examples from the book

☐  Set up or update social media profiles (Twitter/X, LinkedIn, GitHub)

## 9.2 Community Outreach

☐  Post announcement in Rust community forums (users.rust-lang.org)

☐  Share on relevant Reddit communities: r/rust, r/blockchain, r/cryptocurrency

☐  Post on Hacker News (Show HN) on launch day

☐  Reach out to Rust newsletters (This Week in Rust, Rust Times)

☐  Contact blockchain/crypto newsletters and blogs for potential reviews

☐  Post on LinkedIn with a professional announcement

## 9.3 Review Copies

☐  Identify 10–20 potential reviewers (Rust bloggers, blockchain educators, tech reviewers)

☐  Send advance EPUB copies with a personalized note

☐  Ask for honest reviews on Amazon and Goodreads

☐  Prepare a press kit: cover image, author bio, 1-page summary, sample chapter

## 9.4 Content Marketing

☐  Write 2–3 blog posts based on book chapters (teasers, not full content)

☐  Create a GitHub repository with sample code from the book

☐  Record a podcast episode or seek guest spots on Rust/blockchain podcasts

☐  Prepare a conference talk proposal based on the book’s content

# 10. Launch Day Checklist

Timing Note Coordinate all platforms to go live on the same date. IngramSpark typically needs 6–8 weeks to propagate to all retailers, so plan accordingly. Amazon KDP and Apple Books can be published within 24–72 hours.

## 10.1 Platform Verification

☐  Verify the book is live on Amazon (both Kindle and paperback if using KDP Print)

☐  Verify the book is live on Apple Books

☐  Verify the book appears in the Ingram catalog

☐  Verify all "Look Inside" previews are working (Amazon)

☐  Verify purchase links work and lead to the correct book

☐  Check that all metadata (title, author, description) is correct on every platform

## 10.2 Announcements

☐  Post launch announcement on all social media channels

☐  Send email to your mailing list (if applicable)

☐  Post on Hacker News (Show HN: My Book on Building a Blockchain in Rust)

☐  Post on Reddit communities with links

☐  Notify reviewers that the book is now live

☐  Update your GitHub profile and any project READMEs with book link

## 10.3 Day-One Monitoring

☐  Monitor Amazon listing for any display issues

☐  Check for early reviews and respond graciously

☐  Monitor social media mentions and engage with readers

☐  Track sales across all platforms

# 11. Post-Launch Monitoring

## 11.1 First Week

☐  Monitor daily sales across all platforms

☐  Respond to reader questions and feedback

☐  Address any errata reported by readers

☐  Track Amazon sales rank in relevant categories

☐  Follow up with reviewers who received advance copies

## 11.2 First Month

☐  Compile initial sales data and compare to projections

☐  Evaluate which marketing channels drove the most sales

☐  Consider adjusting pricing if sales are below expectations

☐  Plan second wave of marketing (guest blog posts, podcast appearances)

☐  Start an errata document for a future second printing if needed

## 11.3 Ongoing

☐  Monitor for Rust language updates that may affect code examples

☐  Engage with readers on GitHub issues related to book code

☐  Consider supplemental content (blog series, video course, updated edition)

☐  Track cumulative royalties and tax implications

☐  Update book description seasonally to keep it fresh in search results

# 12. Appendix: File Inventory

Complete inventory of project files relevant to the publication process.

## 12.1 Print-Ready Files (book-print/)

| File | Upload To | Notes |
| --- | --- | --- |
| interior.pdf | IngramSpark (interior), KDP Print (interior) | Crop marks + bleed, no back cover |
| cover-full-wrap.pdf | IngramSpark (cover) | Full wrap: front + spine + back |
| cover-full-wrap.png | Backup / marketing | 300 DPI PNG version of wrap |
| cover-front.png | KDP (cover), Apple Books, all stores | Store listing cover image |
| cover-back.png | Marketing materials | Back cover with ISBN barcode |
| rust-blockchain.epub | Apple Books, Google Play, Kobo | Syntax-highlighted code |
| rust-blockchain-kindle.epub | Amazon KDP (Kindle) | Plain monospace for Kindle compatibility |

## 12.2 Project Documents (book-draft/_project/)

| File | Purpose |
| --- | --- |
| Pricing-Strategy.docx | Detailed pricing analysis and royalty calculations |
| LATEX-CONVERSION-PLAN.pdf | 22-page conversion plan, all phases marked COMPLETE |
| Book-Marketing-Syndication-Plan.docx | Marketing strategy document |
| Cover-Image-Recommendations.docx | Cover design specifications and guidelines |
| Publication-Launch-Guide.docx | This document |

## 12.3 Source Files (book-latex/)

| File / Directory | Purpose |
| --- | --- |
| main.tex | Master document (back cover commented out for IngramSpark) |
| preamble.tex | Page setup, crop marks, bleed, IngramSpark specs |
| chapters/ | 33 chapter .tex files |
| images/ | All figures and diagrams |
| backmatter/ | Appendices, glossary, index |

## 12.4 Generation Scripts

| Script | Purpose | Command |
| --- | --- | --- |
| gen_cover_wrap.py | Generate IngramSpark cover wrap | python gen_cover_wrap.py |
| gen_epub.py | Generate both EPUB versions | python gen_epub.py |
| gen_plan_pdf.py | Regenerate conversion plan PDF | python gen_plan_pdf.py |

────────────────────────────────────────

End of Publication Launch Guide

Good luck with the launch!